## Sheet1
Event organisation
Template Timetable
| Needs Assessment | Budget | Funding | Organising Committee | Faculty | Programme | Event promotion | CME accreditation | Participants | Logistics | Post event feed-back to partners | Learners feed-back | Follow up with learners | Outcome measurement
-24 to 18 months | Milti-source data collection, for example: - Surveys - Scientific committees / focus groups - Expert opinion / expert panel - Evaluation results from other activities - Statistical or epidemiological data / results - Peer-review literature / internet search - Database analysis (eg changes in diagnosis or prescriptions) - Syllabus of similar programmes - Audits (patient care, incident reports, mortality/morbidity data..) - New regulations, guidelines, treatments, technology.. |  | Explore funding possibilities and check application deadlines: - European Scientific Societies - National Scientific Societies - Governmental agencies - Universities, hospitals - Pharmaceutical companies - Equipment companies | Identify Organising Committee members | [5 empty] | Assign individuals to organise the event
-18 to 12 months | Analysis of collected data: - What are the gaps? - What are the most appropriate educational methods to bridge the gaps? - What is the target audience? - What is the educational goal? - How will the educational methodology be evaluated? | Prepare budget and determine: - What will the participant fee be? - Will extra funding or sponsorship be necessary? | Apply for funding | Organising Committee to: - review and validated needs assessment analysis - approve education outcome - approve education methods - identify faculty - approve programme - approve budget - approve funding/sponsorship applications | Recruit speakers and send them the following: - informaiton on the event topic, time, date, venue - information on the event educational outcome - information on the event educational methods - proposed topic for their talks - proposed duration, time and date of their talks | Start desiging the event programme | Explore means to promote event depending on budget: - through partner hospital and universities - through the organising committee and faculty - through National Respiratory Society - through the Medical Chamber - through the European Respiratory Society - through accreditor's website - advertisment in journals - through other events and congresses - through sponsor | Explore possibility for CME accreditation for the event In particular, pay attention to: - submission deadlines - accreditation guidelines - sponsorship guidelines - guidelines on the use of sponsors name and logo on promotional items |  | Reserach best possible: - potential city - potential venue - potential date Taking into account: - cost of living, lodging and local transport in the selected city(ies) - closest airport - flight frequency and prices from/to other European countries Check: - that no other major events are taking place at the same time in the identified city/venue - lodging possibilities in the selected city(ies) - tourist attractions in the selected city(ies)
-12 to 6 months |  |  | Finalise contracts with funders and sponsors If you plan to request for CME accreditation, pay particular attention to accreditor's sponsorship guidelines before signing contracts |  | Further information sent to speakers once they have agreed to participate: - instructions regarding time allocated for their presentation, for discussion and/or practical exercises - request to sign COI form - information regarding honorarium and/or travel expense policy - deadline to produce their powerpoint | Draft programme Speakers should have been invited and most should have confirmed attendance, although changes can happen at any given moment | Design and print promotional material, if any: - advertisment - leaflets - website Start promoting the event | Explore possibility for CME accreditation for the event Pay attention to: - submission deadlines - accreditation guidelines - sponsorship guidelines - guidelines on the use of sponsors name and logo on programme and promotional items | Start participant registration | Select event venue and start negotiating contracts for: - venue - lodging - catering - technical support and material required (beamer, microphone, recording, voting pads, Wi-Fi/internet, barcode reader, etc.) - signage If desired / needed: - PCO and/or partner travel agent - transport company for transfers - restaurants / social events - technical support - printing company (signage, promotional material, menus, etc.) - other contractors (conference bags/promotional items, poster boards, displays, etc.)
-6 to 3 months |  |  |  |  | Logistical information to speakers: - information on the city - information on the venue - information on the lodging - information on potential transfers to/from airport - information on public transports - information on social events Request speaekers to initiate their travel and accommodation bookings | Final programme Unless emergency/last minute unforeseen issue by speakers, programme should be finalised | Ongoing promotion of the event | Collect information and documents necessary for the accreditation request - Scientific/Organising Committee COIs - Director's declaration - Programme - Facutly list - Learners feed-back form | Ongoing participant registration | Finalise contracts with all partners and contractors Sart travel and accommodation bookings for faculty and participants Either in-house or through partner travel agent or PCO |  | Design learners feed-back form This is needed for CME accreditation
-3 to 2 months |  |  |  |  | Reminders to speakers: - sign COI form - instructions and deadline to produce powerpoint - instructions and deadline to produce handout material - information on travel and accommodation - travel and accommodation bookings to be finalised |  | Ongoing promotion of the event | Apply for CME accreditation | Ongoing participant registration | Travel and accommodation bookings for faculty and participants (continued)
-2 months |  |  |  |  | Collect last documents for hand-out material |  | Ongoing promotion of the event | Event accredited? | Ongoing participant registration | Start compiling the rooming list for hotel(s) Finalise arrangements with contractors - technical support - recording - technical equipment rental - etc... Finalise signage - organise printing - organise shipment if necessary Handout material - Collect and collate last missing documents for the handout material
-1 month | [6 empty] | Ongoing promotion of the event |  | Ongoing participant registration | Finalise accommodation and travel arrangements Finalise handout - print - organise shipment Finalise and print onsite material - name tags/badges - participants signing sheets - learners feed-back / evaluation forms - attendance certificates |  |  | Advise learners that - they will be asked to complete a feed-back form at the end of the event - they will be asked to complete a follow up form six months after the event If desired, ask learners to sign - a "commitment to change" - a "commitment to complete the learners feedback/follow up forms"
-2 weeks | [8 empty] | Ongoing participant registration | Prepare shipment of onsite material - all printed material - office supply - brochures - posters - voting pads/cards - pointers - electrical adaptors
-1 week | [8 empty] | Ongoing participant registration | Finalise arrangements - send final rooming list to hotel - send final list of participants incl. Dietary requirements to caterer / restaurant - send final list of participants incl. Schedule to the transport company (if transfer organised) - schedule time onsite with your contact persons at the venue and any other partners - remind venue and hotel of important information (timetable, room set-up, required equipment, list of VIPs, etc.) - collate and copy last version of the presentations on computer, external disk or USB key
-1 day | [9 empty] | Organisers/staff arrive onsite Visual inspection of the venue - check room set-up - check lighting - check audio-visual equipment - identify closest emergency exits, restrooms, elevators, stairs, etc. Meet with all partners to go through last details - venue staff - caterer - hotel staff - contractors Set-up - registration area (if any) - signage - poster / communication boards Check that faculty has arrived
day 1 | [9 empty] | If faculty has not arrived, re-organise programme and let meeting chairs know At the venue, check - room set-up - audiovisual equipment - light - room temperature Distribute - name tags/badges - handout material - brochures/promotional material - programme Assist faculty Upload presentations Check catering is delivered on time Take note of any issue for report
day 2-x | [9 empty] | As for day 1 Collect learners feed-back forms on the last day of the event |  | Ask learners to complete their feed-back form Collect completed forms
+1 month |  |  |  | Send to organising committee - thank you letter - certificates (committee/attendance + CME) - post-event report | Send to faculty - thank you letter - certificates (faculty/attendance + CME) |  |  | Send post-event report to accreditor | Send to participants: - certificates (attendance + CME) - reminder that they will be contacted for further feed-back on learning outcomes at +6 months |  | Collate comments on logistic organisation from - staff onsite - faculty - learners Send feedback to partners - venue - hotel - caterer / restaurant - contractors, incl. PCO, travel agent, printer, technical support, transport company, etc. | Analyse learners' feed-back form results Include learners' feed-back in post-event report Write and send event post-event report to - CME accreditor - Scientific/organising committee
+3 months |  | Finalise budget (actual vs budget) | [10 empty] | Design follow up form
+6 months | [12 empty] | Send follow up form to all participants Collect results Analyse results | Feed-back analysis results into the needs assessments/outcome measurement matrix/analysis - including results of learners' feed-back - including results of learners' follow up forms